{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["Sheet1","Sheet1(副本)"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":21,"n_cols":22,"rows_kept":21,"hidden":true,"merged":[[0,0,0,21],[1,0,2,0],[1,1,1,3],[1,4,1,6],[1,7,1,9],[1,10,1,12],[1,13,1,15],[1,16,1,18],[1,19,1,21]],"flags":["formulas_cached_only"]}
["第16周每日风险预计"]
["地市","周一（4月10日）",null,null,"周二（4月11日）",null,null,"周三（4月12日）",null,null,"周四（4月13日）",null,null,"周五（4月14日）",null,null,"周六（4月15日）",null,null,"周日（4月16日）"]
[null,"二级","三级","四级及以下","二级","三级","四级及以下","二级","三级","四级及以下","二级","三级","四级及以下","二级","三级","四级及以下","二级","三级","四级及以下","二级","三级","四级及以下"]
["建设分公司",1,51,19,1,50,22,1,50,19,0,51,20,1,50,20,0,52,19,1,50,17]
["合肥",1,9,25,0,9,25,0,9,25,0,9,25,0,9,25,0,9,25,0,9]
["马鞍山"]
["芜湖",0,7,7,0,8,8,0,9,8,0,9,8,0,9,8,0,9,8,0,9,8]
["安庆",0,5,18,0,7,18,0,7,18,0,7,18,0,7,18,0,7,18,0,7,18]
["淮南",1,3,9,1,2,9,1,2,9,1,2,8,0,2,8,0,2,8,0,2,8]
["宣城",0,10,19,0,11,18,0,12,20,0,12,19,0,11,18,0,9,16,0,10,18]
["阜阳"]
["铜陵"]
["蚌埠"]
["滁州",0,8,16,0,8,17,0,8,17,0,8,16,0,7,15,0,7,14,0,7,18]
["六安",0,11,21,0,12,22,0,11,23,0,10,22,0,13,21,0,12,21,0,13]
["淮北"]
["宿州",0,4,46,0,4,49,0,5,49,0,6,47,0,6,47,0,6,47,0,7,46]
["池州",0,12,14,0,12,15,0,11,14,2,11,13,1,11,14,1,11,13,1,11,14]
["黄山"]
["亳州",null,16,40,1,16,40,0,16,40,0,16,40,0,16,40,0,16,40,0,16,40]
["合计"]

{"sheet":"Sheet1(副本)","index":1,"n_rows":2,"n_cols":20,"rows_kept":2,"flags":["formulas_cached_only"]}
["单位","安全编码","在施工程名称","在施工程作业范围","工程规模","安全总监","建设单位","监理单位","施工单位","工程位置","实际开工时间","计划竣工时间","当前工程进度","当前工程状态","当前风险等级","当前风险判断理由","梳理时间","下次梳理时间","下次梳理重点","备注"]
["13120013508G01","24-11-XL-0500-22-010-00","安徽芜湖1000kV变电站～铜北500kV线路工程","否","线路总长约79.1km，全线双回路架设。杆塔总数188基，其中直线塔110基，耐张塔78基。无拆旧","黄蒙18110995457","建设分公司","安徽电力工程监理有限公司","安徽送变电工程公司","安徽省芜湖市繁昌区","2022-11-25","2023-06-30","基础完成187基；组塔完成119基；架线完成15,629km","基础阶段、组塔阶段、架线阶段","中风险","近期有二级及三级风险作业","2023-04-13","2023-05-15","该工程近期作业包含8+2工况，已安排值班员重点关注。/该工程近期进行组塔及架线作业，应重点关注。4月中旬有二级风险跨越",123]